## Sheet1
SR.NO | TASK NAME | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
1 | RESEARCH AND IDEATION | bar: WEEK 3
2 | PROTOTYPING | bar: WEEK 4
3 | CORE AR FUNCTIONALITY DEVELOPMENT | bar: WEEK 5 to WEEK 7
4 | USER INTERFACE REFINEMENT | bar: WEEK 8 to WEEK 9
5 | USER TESTING AND OPTIMISATION | bar: WEEK 10